## EndToEnd_report
WF no. | Packaging type | WF status | Order bom component | Current step | Current assign | Current dutaion | Current due date | So no. | Brand | Additional brand | Product code | Prod./insp. memo | RD reference no. | Production plant | Sold to | Ship to | Country | Port | In transit to | SO create date | RDD | PA owner | PG owner | Request form/checklist form no. | Step | Assign | Duration | Extend Duration | Start date | Start time | End date | End time | Used days | Due date | Due date time | Total(days) | Reason code | Project name | Creator | Marketing
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | Assigned PA | Natthida Sutrung |  | 31/03/2021 18:31:21 | 500439112(600) | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 | G8HXSA NNFM3HL2L |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China | SHANGHAI,CHINA/ASIA |  | 19/11/2020 | 01/05/2021 | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Assigned PA | Natthida Sutrung | 10.0 |  | 17/03/2021 | 18:31:21 |  |  | 0 | 31/03/2021 | 18:31:21 | 25 |  | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | PA ask for dieline and assign vendor | Pitukarn Thirapatjinda | 2.0 |  | 18/03/2021 | 15:39:11 | 18/03/2021 | 18:29:30 | 0 | 22/03/2021 | 15:39:11 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Waiting for MK confirmation | Chinapat Amornsak | 1.0 |  | 22/03/2021 | 17:05:09 | 24/03/2021 | 12:24:10 | 2 | 23/03/2021 | 17:05:09 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:14 | 25/03/2021 | 10:21:57 | 1 | 25/03/2021 | 14:08:14 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:14 | 25/03/2021 | 10:21:58 | 0 | 25/03/2021 | 14:08:14 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:14 | 25/03/2021 | 10:21:58 | 0 | 25/03/2021 | 14:08:14 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:14 | 25/03/2021 | 10:21:58 | 0 | 25/03/2021 | 14:08:14 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:14 | 25/03/2021 | 10:21:58 | 0 | 25/03/2021 | 14:08:14 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:14 | 25/03/2021 | 10:21:58 | 0 | 25/03/2021 | 14:08:14 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:14 | 25/03/2021 | 10:21:57 | 0 | 25/03/2021 | 14:08:14 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Waiting for customer approval print master | Chinapat Amornsak | 4.0 |  | 25/03/2021 | 13:47:36 | 18/04/2021 | 15:06:59 | 16 | 31/03/2021 | 13:47:36 |  |  | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | QC check regulation/formula | Yonradee Thawornwattanasirikul | 2.0 |  | 16/04/2021 | 17:47:15 | 22/04/2021 | 14:49:14 | 4 | 20/04/2021 | 17:47:15 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:51:38 | 19/04/2021 | 10:51:13 | 1 | 19/04/2021 | 17:51:38 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:51:38 | 19/04/2021 | 10:51:13 | 0 | 19/04/2021 | 17:51:38 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:51:38 | 19/04/2021 | 10:51:13 | 0 | 19/04/2021 | 17:51:38 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:51:38 | 19/04/2021 | 10:51:13 | 0 | 19/04/2021 | 17:51:38 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:51:38 | 19/04/2021 | 10:51:13 | 0 | 19/04/2021 | 17:51:38 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:51:38 | 19/04/2021 | 10:51:13 | 0 | 19/04/2021 | 17:51:38 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:51:38 | 19/04/2021 | 10:51:13 | 0 | 19/04/2021 | 17:51:38 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | RD check regulation/formula | Phanngam Kaewruang | 2.0 |  | 17/04/2021 | 07:15:42 | 22/04/2021 | 14:21:43 | 3 | 21/04/2021 | 00:01:00 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | PA send back artwork to MK | Chinapat Amornsak | 1.0 |  | 21/04/2021 | 12:05:53 | 21/04/2021 | 13:13:08 | 0 | 22/04/2021 | 12:05:53 |  | อื่นๆ โปรดระบุ | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | Waiting for customer review | Chinapat Amornsak |  | 27/04/2021 18:43:59 |  | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Waiting for customer review | Chinapat Amornsak | 3.0 |  | 22/04/2021 | 18:43:59 |  |  | 0 | 27/04/2021 | 18:43:59 |  |  | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002155 | L:Leaflet | In process | 5L00C181N000001100 | Waiting for customer approval print master | Chinapat Amornsak |  | 29/04/2021 13:49:12 |  | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Waiting for customer approval print master | Chinapat Amornsak | 4.0 |  | 23/04/2021 | 13:49:12 |  |  | 0 | 29/04/2021 | 13:49:12 |  |  | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002156 |  | Teminated | [6 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung |  | RF-2021-00026959 | Assigned PA [Terminated] | Natthida Sutrung | 10.0 |  | 17/03/2021 | 18:31:23 | 18/03/2021 | 14:16:39 | 1 | 31/03/2021 | 18:31:23 | 1 |  | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | Assigned PA | Natthida Sutrung |  | 31/03/2021 18:31:25 | 500439112(100) | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 | G8HXSA NNFM3IL2L |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China | SHANGHAI,CHINA/ASIA |  | 19/11/2020 | 01/05/2021 | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Assigned PA | Natthida Sutrung | 10.0 |  | 17/03/2021 | 18:31:25 |  |  | 0 | 31/03/2021 | 18:31:25 | 25 |  | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | PA ask for dieline and assign vendor | Pitukarn Thirapatjinda | 2.0 |  | 18/03/2021 | 15:39:17 | 18/03/2021 | 18:30:35 | 0 | 22/03/2021 | 15:39:17 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Waiting for MK confirmation | Chinapat Amornsak | 1.0 |  | 22/03/2021 | 17:05:21 | 24/03/2021 | 12:25:37 | 2 | 23/03/2021 | 17:05:21 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:21 | 25/03/2021 | 10:22:18 | 1 | 25/03/2021 | 14:08:21 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:21 | 25/03/2021 | 10:22:18 | 0 | 25/03/2021 | 14:08:21 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:21 | 25/03/2021 | 10:22:18 | 0 | 25/03/2021 | 14:08:21 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:21 | 25/03/2021 | 10:22:18 | 0 | 25/03/2021 | 14:08:21 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:21 | 25/03/2021 | 10:22:18 | 0 | 25/03/2021 | 14:08:21 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:21 | 25/03/2021 | 10:22:18 | 0 | 25/03/2021 | 14:08:21 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:21 | 25/03/2021 | 10:22:18 | 0 | 25/03/2021 | 14:08:21 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Waiting for customer approval print master | Chinapat Amornsak | 4.0 |  | 25/03/2021 | 13:48:24 | 18/04/2021 | 15:07:15 | 16 | 31/03/2021 | 13:48:24 |  |  | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | QC check regulation/formula | Yonradee Thawornwattanasirikul | 2.0 |  | 16/04/2021 | 17:47:33 | 22/04/2021 | 14:59:00 | 4 | 20/04/2021 | 17:47:33 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:51:48 | 19/04/2021 | 10:52:15 | 1 | 19/04/2021 | 17:51:48 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:51:48 | 19/04/2021 | 10:52:15 | 0 | 19/04/2021 | 17:51:48 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:51:48 | 19/04/2021 | 10:52:15 | 0 | 19/04/2021 | 17:51:48 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:51:48 | 19/04/2021 | 10:52:15 | 0 | 19/04/2021 | 17:51:48 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:51:49 | 19/04/2021 | 10:52:15 | 0 | 19/04/2021 | 17:51:49 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:51:49 | 19/04/2021 | 10:52:15 | 0 | 19/04/2021 | 17:51:49 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:51:49 | 19/04/2021 | 10:52:15 | 0 | 19/04/2021 | 17:51:49 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | RD check regulation/formula | Phanngam Kaewruang | 2.0 |  | 17/04/2021 | 07:16:15 | 22/04/2021 | 14:37:13 | 3 | 21/04/2021 | 00:01:00 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | Waiting for customer review | Chinapat Amornsak |  | 27/04/2021 18:44:07 |  | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Waiting for customer review | Chinapat Amornsak | 3.0 |  | 22/04/2021 | 18:44:07 |  |  | 0 | 27/04/2021 | 18:44:07 |  |  | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002157 | L:Leaflet | In process | 5L00C181N000001200 | Waiting for customer approval print master | Chinapat Amornsak |  | 29/04/2021 13:51:00 |  | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Waiting for customer approval print master | Chinapat Amornsak | 4.0 |  | 23/04/2021 | 13:51:00 |  |  | 0 | 29/04/2021 | 13:51:00 |  |  | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002158 |  | Teminated | [6 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung |  | RF-2021-00026959 | Assigned PA [Terminated] | Natthida Sutrung | 10.0 |  | 17/03/2021 | 18:31:28 | 18/03/2021 | 14:16:58 | 1 | 31/03/2021 | 18:31:28 | 1 |  | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | Assigned PA | Natthida Sutrung |  | 31/03/2021 18:31:30 | 500439112(300) | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 | G8HXSA NNFM3EL2L |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China | SHANGHAI,CHINA/ASIA |  | 19/11/2020 | 01/05/2021 | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Assigned PA | Natthida Sutrung | 10.0 |  | 17/03/2021 | 18:31:30 |  |  | 0 | 31/03/2021 | 18:31:30 | 25 |  | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | PA ask for dieline and assign vendor | Pitukarn Thirapatjinda | 2.0 |  | 18/03/2021 | 15:39:24 | 18/03/2021 | 18:30:59 | 0 | 22/03/2021 | 15:39:24 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Waiting for MK confirmation | Chinapat Amornsak | 1.0 |  | 22/03/2021 | 17:05:32 | 24/03/2021 | 12:26:37 | 2 | 23/03/2021 | 17:05:32 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:26 | 25/03/2021 | 10:22:42 | 1 | 25/03/2021 | 14:08:26 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:26 | 25/03/2021 | 10:22:42 | 0 | 25/03/2021 | 14:08:26 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:26 | 25/03/2021 | 10:22:42 | 0 | 25/03/2021 | 14:08:26 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:26 | 25/03/2021 | 10:22:43 | 0 | 25/03/2021 | 14:08:26 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:26 | 25/03/2021 | 10:22:43 | 0 | 25/03/2021 | 14:08:26 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:26 | 25/03/2021 | 10:22:43 | 0 | 25/03/2021 | 14:08:26 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:26 | 25/03/2021 | 10:22:42 | 0 | 25/03/2021 | 14:08:26 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Waiting for customer approval print master | Chinapat Amornsak | 4.0 |  | 25/03/2021 | 13:49:06 | 18/04/2021 | 15:07:28 | 16 | 31/03/2021 | 13:49:06 |  |  | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | QC check regulation/formula | Yonradee Thawornwattanasirikul | 2.0 |  | 16/04/2021 | 17:47:46 | 22/04/2021 | 17:21:09 | 4 | 20/04/2021 | 17:47:46 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:52:00 | 19/04/2021 | 11:14:26 | 1 | 19/04/2021 | 17:52:00 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:52:00 | 19/04/2021 | 11:14:26 | 0 | 19/04/2021 | 17:52:00 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:52:00 | 19/04/2021 | 11:14:26 | 0 | 19/04/2021 | 17:52:00 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:52:00 | 19/04/2021 | 11:14:26 | 0 | 19/04/2021 | 17:52:00 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:52:00 | 19/04/2021 | 11:14:26 | 0 | 19/04/2021 | 17:52:00 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:52:00 | 19/04/2021 | 11:14:26 | 0 | 19/04/2021 | 17:52:00 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:52:00 | 19/04/2021 | 11:14:26 | 0 | 19/04/2021 | 17:52:00 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | RD check regulation/formula | Phanngam Kaewruang | 2.0 |  | 17/04/2021 | 07:16:54 | 22/04/2021 | 16:21:26 | 3 | 21/04/2021 | 00:01:00 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | Waiting for customer review | Chinapat Amornsak |  | 27/04/2021 18:43:21 |  | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Waiting for customer review | Chinapat Amornsak | 3.0 |  | 22/04/2021 | 18:43:21 |  |  | 0 | 27/04/2021 | 18:43:21 |  |  | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002159 | L:Leaflet | In process | 5L00C181N000001400 | Waiting for customer approval print master | Chinapat Amornsak |  | 29/04/2021 13:51:23 |  | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Waiting for customer approval print master | Chinapat Amornsak | 4.0 |  | 23/04/2021 | 13:51:23 |  |  | 0 | 29/04/2021 | 13:51:23 |  |  | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002160 |  | Teminated | [6 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung |  | RF-2021-00026959 | Assigned PA [Terminated] | Natthida Sutrung | 10.0 |  | 17/03/2021 | 18:31:32 | 18/03/2021 | 14:17:08 | 1 | 31/03/2021 | 18:31:32 | 1 |  | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | Assigned PA | Natthida Sutrung |  | 31/03/2021 18:31:34 |  | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Assigned PA | Natthida Sutrung | 10.0 |  | 17/03/2021 | 18:31:34 |  |  | 0 | 31/03/2021 | 18:31:34 | 25 |  | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | PA ask for dieline and assign vendor | Pitukarn Thirapatjinda | 2.0 |  | 18/03/2021 | 15:39:28 | 18/03/2021 | 18:31:50 | 0 | 22/03/2021 | 15:39:28 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Waiting for MK confirmation | Chinapat Amornsak | 1.0 |  | 22/03/2021 | 17:05:43 | 24/03/2021 | 12:27:25 | 2 | 23/03/2021 | 17:05:43 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:32 | 25/03/2021 | 10:23:44 | 1 | 25/03/2021 | 14:08:32 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:32 | 25/03/2021 | 10:23:44 | 0 | 25/03/2021 | 14:08:32 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:32 | 25/03/2021 | 10:23:44 | 0 | 25/03/2021 | 14:08:32 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:32 | 25/03/2021 | 10:23:44 | 0 | 25/03/2021 | 14:08:32 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:32 | 25/03/2021 | 10:23:44 | 0 | 25/03/2021 | 14:08:32 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:32 | 25/03/2021 | 10:23:44 | 0 | 25/03/2021 | 14:08:32 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 24/03/2021 | 14:08:32 | 25/03/2021 | 10:23:44 | 0 | 25/03/2021 | 14:08:32 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Waiting for customer approval print master | Chinapat Amornsak | 4.0 |  | 25/03/2021 | 13:50:06 | 18/04/2021 | 15:07:40 | 16 | 31/03/2021 | 13:50:06 |  |  | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | QC check regulation/formula | Yonradee Thawornwattanasirikul | 2.0 |  | 16/04/2021 | 17:47:57 | 22/04/2021 | 17:22:47 | 4 | 20/04/2021 | 17:47:57 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:52:10 | 19/04/2021 | 11:11:40 | 1 | 19/04/2021 | 17:52:10 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:52:10 | 19/04/2021 | 11:11:40 | 0 | 19/04/2021 | 17:52:10 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:52:10 | 19/04/2021 | 11:11:40 | 0 | 19/04/2021 | 17:52:10 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:52:10 | 19/04/2021 | 11:11:40 | 0 | 19/04/2021 | 17:52:10 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:52:10 | 19/04/2021 | 11:11:40 | 0 | 19/04/2021 | 17:52:10 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:52:10 | 19/04/2021 | 11:11:40 | 0 | 19/04/2021 | 17:52:10 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Develop print master for customer | 107 บจก.ไทยยูเนี่ยน กราฟฟิกส์ | 1.0 |  | 16/04/2021 | 17:52:10 | 19/04/2021 | 11:11:40 | 0 | 19/04/2021 | 17:52:10 |  | ลูกค้า upload file มาใหม่ (Customer upload new file) | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | [5 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | RD check regulation/formula | Phanngam Kaewruang | 2.0 |  | 17/04/2021 | 07:17:29 | 22/04/2021 | 16:29:28 | 3 | 21/04/2021 | 00:01:00 |  | No reason | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | Waiting for customer review | Chinapat Amornsak |  | 27/04/2021 18:43:15 |  | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Waiting for customer review | Chinapat Amornsak | 3.0 |  | 22/04/2021 | 18:43:15 |  |  | 0 | 27/04/2021 | 18:43:15 |  |  | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002161 | L:Leaflet | In process | 5L00C181N000001300 | Waiting for customer approval print master | Chinapat Amornsak |  | 29/04/2021 13:51:10 |  | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung | Pitukarn Thirapatjinda | RF-2021-00026959 | Waiting for customer approval print master | Chinapat Amornsak | 4.0 |  | 23/04/2021 | 13:51:10 |  |  | 0 | 29/04/2021 | 13:51:10 |  |  | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak
AW-N-2021-00002162 |  | Teminated | [6 empty] | 00C:SOLID GOLD |  | 3GNNFM3EL2L8HXSA20:209.5,208x107 IND MC N TN G GF 24/3OZ-24,3GNNFM3FL2L8HXSA20:209.5,208X107 2P85N IND MOON SAR N TN-24,3GNNFM3HL2L8HXSA20:209.5,208X107 2P85N IND MOON SHR TN-24,3GNNFM3IL2L8HXSA20:209.5,208X107 2P85N INDIGO MOON TN NG-24 |  |  | 1031:SCC Songkla Plant | 10001154:SOLID GOLD PET,LLC. | 20004445:HangZhou YunTong Information Technology Co., Ltd | CN:China |  |  |  |  | Natthida Sutrung |  | RF-2021-00026959 | Assigned PA [Terminated] | Natthida Sutrung | 10.0 |  | 17/03/2021 | 18:31:37 | 18/03/2021 | 14:17:17 | 1 | 31/03/2021 | 18:31:37 | 1 |  | Solid Gold China leaflets shreds 85g | Chinapat Amornsak | Chinapat Amornsak