## Sheet1
Web Base Costing (HF) Meeting
Date: Dec 18, 2019 @ 9.00-15.00 Hrs @ TUM#507
Attendant: K. Akkadet, K. Sunisa, K. Weerawan, K. Anantaya, K. Voravut, K. Chollada, K. Ravirung, K. Piyaluck, K. Suwaphit
No. | รายละเอียดการแก้ไขโดยคุณ Voravut
1 | Request Type | Remove "New Product, Line Extension, Formula Adjustment"
2 | Reject from RD PIC | Add option -> Reject/Approve
Flow: RD PIC -> Reject -> M/AM -> Reject -> MK/PM
3 | Subject of E-mail | Add HF/GPC
Add current status
| E-mail Subject | HF: NEW : Request No. 10201900025 V.00
| Step | Short code
1 | Requester send New Request to RD | HF: NEW : Request No. 10201900025 V.00
2 | M/AM RD assign to RD PIC | HF: ASSIGNED : Request No. 10201900025 V.00
3 | RD PIC reject task | HF: REJECTED : Request No. 10201900025 V.00
4 | RD PIC submit formulation to M/AM RD | HF: FORMULA : Request No. 10201900025 V.00
5 | M/AM RD submit data to Cost Center | HF: COSTING : Request No. 10201900025 V.00
6 | Cost Center accept task | HF: ACCEPTED : Request No. 10201900025 V.00
7 | Cost Center release cost to MK | HF: RELEASED : Request No. 10201900025 V.00
8 | MK accept task | HF:
4 | Content ใน e-mail | Add Sender | คนส่ง email
Add Assignee PM/MK
Remove NW/Product Style
5 | R&D | R&D Name ยังเป็น ID No. ให้แก้ไขเป็น ชื่อ PIC (ตอนนี้แก้ไข TUM แล้ว รอแก้ไขส่วนที่เหลือของ SCC, TUF)
6 | Attached File ใน tab sheet สุดท้าย | แก้ไขให้สามารถเปิด file ได้
7 | Sample Required Date | เพิ่ม Field
8 | Data Admin | Assign to K. Akkadet / K. Voravut
No. | Schedule | Date, Time, Place | Remark
1 | Final data check (prepared by K. Voravut) | Dec 20, 2019 @ 15.00-16.00 Hrs (SM Tower, Room# TBA) | Voravut, Akkadet, Sunisa, Weerawan, Anantaya
2 | Test system | Dec 23, 2019 @ 15.00-16.00 Hrs (SM Tower, Room# TBA) | Voravut, Akkadet, Sunisa, Yanee, Weerawan, Anantaya
3 | Training for Cost Center (TUM, SCC, TUF) + RD SCC | Dec 25, 2019 @ 9.30-11.00 Hrs (TUM # 507) | Akkadet, Voravut
4 | Training for MK/PM (HF) | Jan 7, 2020 @14.00-15.00 Hrs (SM Tower, Room# TBA) | MK, PM, MC (if needed)